## Cover Page
Bill Payment System
Sprint Backlog
|  | Prepared By / Last Updated By | Reviewed By | Approved By
| Name | Akhil Surnedi
| Role | Scrum Master
Signature
| Date | 22/12/2019
Project ID: Car Servicing | BGL19IJ004/project id> |  |  | <SCI.ID> / Ver: <No.>
C3: Protected
:
Controlled copy
Controlled copy
Controlled copy
Controlled Copy

## Instructions
Sprint Backlog <Instructions> Project ID: <Batch code/project id> C3: Protected Controlled Copy
Sprint 1/2
The Sprint sheets has to be filled for each sprint
The Sprint Backlog is the set of Product Backlog items selected for the Sprint, plus a plan for delivering the product Increment and realizing the Sprint Goal. The Sprint Backlog is a forecast by the Development Team about what functionality will be in the next Increment and the work needed to deliver that functionality into a “Done” Increment.The Sprint Backlog is the output of the sprint planning meeting. It is essentially the list of tasks that the Scrum team needs to complete during the sprint in order to turn a selected set of product backlog items into a deliverable increment of functionality.
| Feature Id | List the feature id taken from product backlog that are selected to be completed in the particular sprint.
| Task No | List the number tasks the feature is split into.
| Task | Name the tasks the feature is split into.
| Owner | Name the person responsible for the particular task
| Status | Status of the Task - In progress/Completed
| Original Estimate | Original estimate of the task
| Day 1/2/3/4/5/6 | Task done in Day1/2/3/4/5/6 - Sprint review and retrospective to be held on Day 6
| Total | Summation of the estimation of the per day. To be filled with the total of the estimations filled.
| Charts | Chart is self driven as per the task burned

## Sprint 1
Sprint Backlog Bill Payment System Project ID: BGL19IJ004/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 1.1 | Req 1.01 | When the user clicks on the registration link, system should re-direct to registration form and provide two options: Register as Customer Register as Admin | Akhil | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Completed
FEA 1.1 | Req 1.02 | User to fill the basic attributes: First Name Last Name Age Gender Contact Number Email Address PAN Aadhar Number User Id Password | Akhil | 4 | 3 | 0 | 0 | 0 | 0 | 1 | Completed
FEA 1.1 | Req 1.03 | Clicking ‘Submit’ button should validate the datatype constraints for each field. | Akhil | 3 | 2 | 0 | 0 | 0 | 0 | 1 | Completed
FEA 1.1 | Req 1.04 | User failing to provide information for the mandatory fields be presented with an alert message – ‘Please update the highlighted mandatory field(s).’ Also, highlight the missed out field in red | Akhil | 3 | 2 | 0 | 0 | 0 | 0 | 1 | Completed
FEA 1.1 | Req 1.05 | Post-successful field validation, save the information in the database | Akhil | 3 | 0 | 2 | 0 | 0 | 0 | 1 | Completed
FEA 1.1 | Req 1.06 | Upon saving the information in the database, display the message “New user created successfully | Akhil | 3 | 0 | 2 | 0 | 0 | 0 | 1 | Completed
FEA 1.2 | Req 2.01 | A registered user – is able click ‘Login’ link, after keying in ‘UserID’ & ‘Password’ field and get his credentials authenticated with the existing database entry | Akhil | 4 | 0 | 3 | 1 | 0 | 0 | 1 | Completed
FEA 1.2 | Req 2.02 | If a registered user – is unable to login and get his credentials authenticated, The user is presented with relevant error messages: Invalid User ID (or) Incorrect Password | Akhil | 4 | 0 | 1 | 2 | 0 | 0 | 1 | Completed
FEA 1.4 | Req 4.01 | Admin On login should be able to view the list of newly registered vendors | Akhil | 4 | 0 | 0 | 4 | 0 | 0 | 0 | Completed
FEA 1.4 | Req 4.02 | Admin should be able to view the details of the vendors | Akhil | 3 | 0 | 0 | 1 | 2 | 0 | 0 | Completed
FEA 1.4 | Req 4.03 | Admin should be have rights to accept / send for correction/reject any vendor | Akhil | 4 | 0 | 0 | 0 | 2 | 1 | 1 | Completed
FEA 1.4 | Req 4.04 | Only on accepting, a vendor gets activated and will be available for user | Akhil | 4 | 0 | 0 | 0 | 2 | 1 | 0 | Completed
FEA 1.4 | Req 4.05 | On rejection, a vendor gets de-activated and will not be available for user | Akhil | 4 | 0 | 0 | 0 | 2 | 1 | 0 | Completed
FEA 2.1 | Req 5.01 | Vendor should be allowed to update the registered vendor details as and when required | Akhil | 5 | 0 | 0 | 0 | 0 | 5 | 0 | Completed
|  | Total |  | 49 | 8 | 8 | 8 | 8 | 8 | 8
Sprint Goal
User should be able to register and authenticate. Admin functionalities should be implemented.

## Sprint 2
Sprint Backlog Bill Payment System Project ID: <BGL19IJ004/project id> C3: Protected Controlled Copy
Feature Id | Task No | Task | Owner | Original Estimate | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Status
FEA 1.3 | Req 3.01 | Vendor clicks on the “Register Vendor” button | Akhil
FEA 1.3 | Req 3.02 | Portal to display a form to enter the below details: Name of the Vendor Company Reg. No Vendor Type Address Country State Email Address Contact number Web site Certificate Issued Date Certificate Validity date Year of Establishment | Akhil
FEA 1.3 | Req 3.03 | The display form should have buttons to “Register” or “Reset” the fields | Akhil
FEA 1.3 | Req 3.04 | Clicking on Register button should save the details to the database and display the message “Vendor registered successfully” | Akhil
FEA 1.3 | Req 3.05 | Clicking “Reset” button should clear all the fields and allow Admin to enter new details | Akhil
FEA 3.1 | Req 6.01 | User on login should be able to see the available services | Akhil
FEA 3.1 | Req 6.02 | User should have search option based on category-bill type/vendor | Akhil
FEA 3.1 | Req 6.03 | User on selecting the search criteria, system should list the searched result | Akhil
FEA 3.1 | Req 6.04 | User on clicking the required result from the search result, should be able see the bill details | Akhil
FEA 3.1 | Req 6.05 | Customer to be provided with option to record the type of bills payed regularly: Electricity Telephone DTH Insurance Tax Credit Card Loan account Others | Akhil
FEA 3.1 | Req 6.06 | Based on the type of bill selected, display a form to procure the required details and store in the Database | Akhil
FEA 3.1 | Req 6.07 | Validate the entered details and display a message “Details saved successfully” | Akhil
FEA 3.1 | Req 6.08 | Provide an option if the user wants to set reminders to pay the bills | Akhil
FEA 3.1 | Req 6.09 | Allow the user to choose the frequency of reminder and verify user contact information is updated | Akhil
FEA 3.2 | Req 7.01 | User clicks on the option to Pay Bills | Akhil
FEA 3.2 | Req 7.02 | Portal to display a dropdown button to select the type of bill to be payed: Electricity Telephone DTH Insurance Tax Credit Card Loan account Others | Akhil
FEA 3.2 | Req 7.03 | Post the bill type is selected, Portal to verify the registered/updated information in the Database and the pending amount to be payed. | Akhil
FEA 3.2 | Req 7.04 | If the details not are not available in the database display form based on the selected bill type and allow the user to enter the details | Akhil
FEA 3.2 | Req 7.05 | User to select the payment method: Credit/Debit Card Internet Banking PayTm Google Pay e-Wallet | Akhil
FEA 3.2 | Req 7.06 | Based on the selected payment type, portal to display the form to enter the required details | Akhil
FEA 3.2 | Req 7.07 | Portal to process the payment through vendor payment gateway | Akhil
FEA 3.2 | Req 7.08 | Validate the provided details against the banks and display a message “Bill payement Successful” | Akhil
FEA 3.2 | Req 7.09 | If the entered details do not match display message “Enter correct details | Akhil
FEA 4.1 | Req 8.01 | Allows the user or vendor to report technical issues | Akhil
|  | Total |  | 0 | 0 | 0 | 0 | 0 | 0 | 0
Sprint Goal
Some sprint goal

## Data (hidden)
In-Progress
Completed
N/A